## Sheet1
Date Needed | DOITT/DOE Planned Sprint Release | User Story | Notes from 5/12 Meeting (Tim and Alex) | Related Files (attachments) | Level of Effort (Hours) | Related Changes (e.g. Other systems) | DOE Finder? (Y/N) | Overall Priority
2015-06-22 | 1 | As a Parent, Between 6/22/2015 midnight and 7/11/2015 midnight ('Round 2 application window') I want to be able to click 'apply now' on the splash page or on a Round 2 program's detail box so that I can be directed to SEMS application in a new browser tab. | Proposed Solution: New Field in file labeled 'button_type'. New Values 'Info' or 'Apply' In Prototype- will be delivered in sprint 1 |  |  | add column button_type with values 'apply' or' info' to the prek-location excel file generated by DOE - please keep values lowercase | N | 1
2015-06-22 | 1 | As a Parent, I want to be able to toggle a filter to only view 'Apply Now' sites during round 2 application window, so that I know which sites to rank in my citywide application. | Proposed Solution: New Filter will be called |  |  |  | N | 2
2015-06-22 | 1 | As a parent, I want to see text on the splash page of the Pre-K finder that is specific to the 'round 2 application window' so that I am provided pertinent information each time I access the Pre-K finder tool. | Proposed Solution: Text will have to be supplied and hardcoded for the 'Round 2 application window' |  |  |  | N | 3
2015-06-22 | 1 | As a Parent or DOE staff member, I want to be able to search by 'Program Code', so that I can find a specific program even if I do not know the program name | In Prototype- will be delivered in sprint 1 |  |  |  | Y | 4
2015-06-22 | 1 | As a parent, I do not want to have to clear my browser cache in order to see new programs added to Pre-K Finder, so that I am confident I am seeing the most up to date information about what programs are available at any given time. | Proposed Solution: Change CDN Tag Refresh rate from daily to hourly |  |  |  | N | 5
TBD | 2 | As a DECE Staff member, I want to be able to change the text on the splash page at anytime, so that I can provide parents and other users with the most up to date Pre-K finder instructions. | See Carto DB Prototype |  |  |  | N | 6
TBD | 2 | As a DECE Staff member, I want to be able to change the application period start and end date, so that I can control when parents have the ability to click the 'apply now' button. | See Carto DB Prototype |  |  |  | N | 7
TBD | 2 | As DECE Staff Member, I want to be able to add or remove programs from the Pre-K finder by uploading data to a specific directory, so that I do not need to have the GIS data reconciled by DIIT before manually sending a file the to DoITT GIS team. | See Carto DB Prototype |  |  |  | N | 8
TBD | 1 | As a parent, I want to be able to click a button that re-orients the Pre-K finder map around my current location (Only If have allowed my browser to use my current location), so that I can continue to search for program closest to my location. | In Prototype- will be delivered in sprint 1 |  |  |  | N | 9
TBD | 1 | As a parent, I want to be able to change the language of the Pre-K finder to one of the 10 DOE supported languages, so that the I can use it if I do not read English proficiently. | In Prototype- will be delivered in sprint 1 |  |  |  | Y | 10
TBD | TBD | As a parent, I want to be able to change the language of the 'Get in Touch' form to one of the 9 DOE supported languages, so that the I can use it if I do not read English proficiently. | May need to hold this enhancement as DOE policy does not allow google translate for forms, translating the map is priority 1 and acceptable. |  |  |  | Y | 11
TBD | 1 | As a parent, I want to be able to input my child's DOB into the get in touch form via separate fields for day, month and year (year must = 2011) , so that I enter the DOB correctly. | In Prototype- will be delivered in sprint 1 |  |  |  | N | 12