## Requirements
ID | Scope | Requirement | GIS Notes and Questions | DP et al. responses | DoITT 2/26 | Per 02/26 meeting | Status | Signoff | Notes
1 | Form | Remove "Parent Choice" Section from the Form completely. (And from the Submission Review screen.) Note: The new form then will be more general, and does not auto-populate with a specific Pre-K site depending upon where the parent accessed the Form from. | Without the ability to select a preferred program, what is the point of the map? As a parent I would find it frustrating to go through the process of selection only to have to provide it later verbally. Seems a simple message "This is NOT an application" may suffice if that is the fear. | Map lets you see sites near to a given location (e.g. home, work). Still has value even if you are not sending a message to a particular program. This is a business decision that was escalated up. | seems redundant to have "Apply" and/or "Get in Touch" buttons on each school row and popup if they don’t do anything special. One of each on the screen somplace makes more sense to me. Either have them include the school with the form submission or get rid of school-specific buttons. | ok
2 | Form | Remove text at bottom of Form that reads "I understand that daily attendance and promptness are required. I must arrange for a responsible adult to bring my child to school and pick him/her up daily. I understand that no transportation is provided." |  |  | OK | DOE to provide replacement text for the bottom of the form
3 | Form | Remove "City" field from Form. (And from showing on the Submission Review screen.) |  |  | Ok | ok
4 | Form | Re-arrange layout of House Number, Street Name, and Apt field to be on one line. Shorter text field for House Number. (We want make it less likely that a parent will enter their House Phone number in that field, which we have seen previously). Text fields for Street Name and Apt can be shortened as well. | It is far better for consistency and accuracy to have separate. If not, it requires working out a design that functions on all devices | Can shortening the House Number field be done at least? I willing to strip down the requirement to that. | OK | ok
5 | Form | Put a Help "?" icon next to the House Number field. If the user clicks on that "?" Icon, then a bubble pops up to say "If you live at 52 Chambers Street, the House Number is 52" | Requires working out a design that functions on all devices - not likely to be room for icon - how about placeholder values to illustrate. | ok - lets go with the placeholder idea |  | ok |  |  | Willing to take recommendations here
6 | Form | Place an asterisk (*) next to each required field on the Form. All fields are required except for "Apt". Indicate somewhere on the Form that an asterisk indicates a required field. | Seems unnessary since the only field NOT required now is apt - realestate issue on mobile | ok - but please make sure that user cannot get to the submission confirmation page unless they have filled in all those required fields. The Red text should come up pointing out why we are not letting them submit the form yet. | Ok. Moving forward, since this is a DOE form, edits should be made by DOE. | ok - all required fields needed to submit
7 | Form | Tighter data validation that doesn’t not allow user to get to the Submission Review screen. For example: User is able to enter an 11+ day and evening phone number and still get passed on to the Submission Review form. Can we just limit the phone number field(s) to 10 characters max? Currently the only thing preventing movement on to the Submission Review screen is if a parent leaves required fields NULL. | Need all desired validation rules not just examples. Example: phone number limited to (###) ###-####, list all other validation rules. | Phone numbers: ########## (10 numbers) | OK | ok |  |  | Overall, we'd like the parent to not get to the Submission Review screen unless they have entered valid data for all the required fields.
8 | Form | Tighter data validation on the DOB field. We were able to successfully submit a DOB of "13/01/2011" and "09/09/9999" yesterday. | What is the rule specifically? Only DOB after what and before what? How does this rule apply in any given year? | For DOB, I'm willing to say any valid mm/dd/yyyy date from 01/01/2010 up to 12/31/2015 | This rule doesn't caputure future years. We will externalize the rule in a javascript file to be hosted at DOE that can be changed by DOE in the future. We will send a file to for DOE to host in staging soon. | ok
9 | Form | Restrict zip code field to five digits (it currently accepts zips of random lengths) |  |  | OK | ok
10 | Form | On the Form submission confirmation screen, replace "Pre-K For All" with "Pre-K for All". The phrase appears twice there. |  |  | OK | ok
11 | Form | On the Form submission confirmation email, replace the text that currently says "Please remember to visit nyc.gov/prek after March 16, 2015 to apply for the upcoming school year." to read "Please remember to visit nyc.gov/prek between March 16 and April 24, 2015 to apply for the 2015-16 school year." |  |  | OK | DIIT team to do. Slight modification of text coming from DOE.
12 | App | Add the "Get in Touch" button (leading to the generic Form) to the District School entries on the List |  |  | OK | ok |  |  | Ideally requirements 12-14 could get implemented ahead of March 16
13 | App | Add the "Get in Touch" button (leading to the generic Form) to the District School bubble arrived at via the "Map" function | only district school popup or all schools? | all sites should have this. Only Early Ed Centers currently do. | OK | ok
14 | App | Add a same "Get in Touch" button to the top navy blue banner of the Pre-K Finder. Same formatting as on the List except Orange background, White lettering, and highlight hovering. Positioned at center. Clicking this button will lead parent to the information Form. | The app is a single web page that serves all devices. This requirement will be difficult on mobile due to space limitations. Maybe a landing page and a button under the map controls that redisplays landing page? | We would need to see what you mean here. The current mobile does use a lot of space just for the map/list icons and the "Pre-K Finder text" | Screenshot of proposed design on "Splash Page" worksheet | ok on splash page. DOE providing text and button color suggestions.
15 | App | We need to add a new program type filter called "5-Hour", in addition to the ones already there for "Half Day", "Full Day" and "All". User should be allowed to filter on 1-2 program type options at a time (e.g. parent wants to look at all 5-Hour and Half Day programs). Data Integration will require that we label each site with the program type(s) that it offers. | nothing in data currently maps to 5hr prog. Need to at least know what the value of the day_length field for 5hr will be | yes we will be adding that to the data and provide that information | We cannot code to future date without at least knowing what the schema will look like. What will be the value in the DAY_LENGTH field for 5 hour? | Data being provided by DOE
16 | App | We need to add a new Site type filter called "Charter Schools", in addition to the ones already there for "District Schools", "Early Ed Centers" and "All". User should be allowed to filter on 1-2 site type options at a time (e.g. parent wants to look at all Charter Schools and Early Ed Centers). Data Integration will require that we label each site with its Site type. | nothing in data currently maps to charter school. Need to at least know what the value of the prek_type field for charter school will be… also will this new school type have a different color icon? | yes we will be adding that to the data and provide that information. I suppose new color would be green in keeping in line with DOE colors | When will be receive the data? | Sample data COB 02/27 from DOE
17 | App | "Details" Button. Currently if a user clicks the details button on the site, the cell shifts down to display the seat capacity for FD and HD seats. The ask is this now: When the user clicks the "Details" button in the enhanced App, we would like a new box to flip open to the left of the original site cell to display a good deal of more information about the site. As this will be new data that the App has not displayed before, we will also have to build this into the Data Integration piece of the data that is send to DoiTT on a regular basis. Please see attached for our mockup of how that should look. | The app is a single web page that serves all devices. This requirement will be difficult on mobile due to space limitations. Another option would be to replace the summary content in the list or popup with the detail info and a bacck button or close button. not all data elements are available in the current data set. is this for the public or internal use? | Data is public use. Yes we need to provide that data still. We would need to see what you mean here with your other option proposed. Possibly when user hits details, the shift down function would just extend additional rows beyond the current one row for seat availability? | We can design something that works. Buit without a schema containing the names of fields for new values displayed in the mockup there is no way to even start on this. | Sample data COB 02/27 from DOE. OK on keeping details in the slidedown. |  |  | Please see attached
18 | App | We would also like that same Details button added to the site bubble arrived at via the "Map" function | see comments on 18 | which comments on 18? | Was meant to say "see comments on 17"… new note on 17 also applies here. We need the data now | TBD. A nice to have if possible.
19 | App | We should elimate all references to Calling 311 on some sites, although lets keep that space for displaying different information (see below) | this was orginally a last minute hack fix for last year that aaded this text to the scool name. The schema should be modified to include a special message field and the code modified to display the message if present. Data would be provided according to new schema | ok |  | ok
20 | App | By March 16, we are only going to be displaying sites in the Pre-K Finder open for the 2015-16 school year. For new sites coming on, we would like to use the space vacated by the Calling 311 to have the App display "Opening in September 2015". Data Integration will require that we send to DoITT which sites are new. | see comments on 19 | ok |  | Using "NOTE" field to capture this (or any other) information we want to display about the site. Color of text TBD.
21 | App | Add to the banner at the top "(for the 2015-16 School year)" after "Pre-K Finder". Probably in a different font type and/or size. |  |  |  | ok
22 | App | Currently the Pre-K Finder only allows a parent to search by Address. We would like the parent to be allowed to search by Site Name as well. | is this for the public or internal use? Would require a button to toggle btwn search types - see http://maps.nyc.gov/crime | public use. Yes something like the crime site, to be able to search by address or site name |  | DoiTT to change from Search by "School" to Search by "Program"
23 | App | Currently, if you click on a Site in the map, the corresponding sidebar List does not change (assumedly it stays focussed on your current GPS location). Could the List dynamically refresh to show the sites closest to the Site that the parent has chosen on the map? | It can be resorted by distance from currently selected site, but this may not be inuitive. How about scroll to current site? | not sure what this scrolling would look like. Again, we list this a "nice to have" | Will be left for after 3/16 | ok, possiblly for post 3/16 |  |  | This is a "Nice to Have"
|  | The followinq requirements are what need to go-live on the morning of March 16th: | Not really sufficient time to get these out by 3/16 with proper testing on all devices - especially since many of the requested changes cannot be made to meet all devices as identified in these comments | having this in place by 3/16 is not optional | Meaning everything above is nice to have?
24 | App | On the morning of March 16th, the "Get in Touch" button on the top banner (if it exists yet) should change to read "I still would like more information about Pre-K". Size of the button might need to increase, and it should shift to slightly left of center. | see comments on 14 |  | Screenshot of proposed design on "Splash Page" worksheet | ok on splash page. DOE providing text and button color suggestions.
25 | App | On the morning of March 16th, a new button should appear on the top banner, slightly right of center, that should read "I am ready to apply for Pre-K". When the parent clicks on that button, a new tab should open up in their browser to the following URL: www.semsnycdoe.com/parentsite | see comments on 14 |  | Screenshot of proposed design on "Splash Page" worksheet | ok on splash page. DOE providing text and button color suggestions.
26 | App | On the morning of March 16th, for all District Schools and Early Ed Centers offering Full Day seats, the "Get in Touch" button in their List cell should change to read "Apply Now". If a parent clicks on that Apply button, a new tab should open up in their browser to the following URL: www.semsnycdoe.com/parentsite | what are the dev and stg urls? is there a rule that can applied to this requirement that avoids the need for a code change next year? (i.e. between certain dates the button has one label vs another) - will this date be the same every year? Is there a rule that can be applied (i.e. btwn 3nd Monday of march and 4th fri in april) | Dates will likely be somewhat different every year. I'm not aware of a rule we could put in place right now for future years. There will every year be a start date and and end date, which we communicate well in advance though. I do not know the dev and stg urls. | We will externalize the rule in a javascript file to be hosted at DOE that can be changed by DOE in the future. We will send a file to for DOE to host in staging soon. | ok - not clear if this is to put in place for future years or if javascript file needed for March 16th this year
27 | App | On the morning of March 16th, for all Charter Schools, and for Early Ed Centers offering only Half Day or 5-Hour seats, the "Get in Touch" should remain as such and still point to the Information Form. | see comment on 26 |  |  | ok
28 | App | On the morning of March 16th, in the upper right corner of the top banner, to the left of the Map/List button, we would like a link to display “View the Pre-K Directory for More Info” and if a user clicks on that link a new tab opens in their broswer to the following URL: http://schools.nyc.gov/ChoicesEnrollment/PreK/Resources/default.htm | how many buttons are going in the banner now? Also, new tabs don’t work in iOS standalone mode that is why we have all of the problems with the form in an iframe. If user creates a desktop shortcut to finder app in iOS and clicks a link or button that opens in a new tab they cannot get back to the finder app without going back to desktop and starting over. | there are none right now. We are proposing 3 buttons in the banner during the Application period. This one, plus the "I still need more info about Pre-K", and the "I'm ready to apply for Pre-K". It sounds like for the mobile devices, the main issue is just real estate on the banner? | Splash screen is really the only workable solution. Screenshot of proposed design on "Splash Page" worksheet. | ok on splash page. DOE providing text and button color suggestions.
29 | App | On the morning of April 25th, the application period in SEMS has ended. We should then revert back to the "Get in Touch" button at the top center of the screen and each site cell should revert back to the "Get in Touch" button. All those Get in Touch buttons lead the parent to the Information Form. | see comment on 26 |  |  | ok
Note on E17: Keane, Tim: Since the value for Charter School that will appear in PREK_TYPE has not been provided I am assuming it will be CHARTER. Let's make it that in future data submissions.

## Questions
ID | Item
1 | Is the schools data correct?
2 | Is the number of seats correct?
x

## Splash Page
Initial View | Map View | Map View
provides room for descriptive text tobe provided by DOE. Info icon as que to info button on map view. | Info button allows for the redisplay of the splash page. | Splash page redisplayed after clicking Info button.